## Customer Project Gantt
Phase | Task ID | Task Name | People/Roles Involved | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
1.0 Requirements Engineering | 1.1 | Site Assessments & Elicitation (5 Sites) | Mr. Marcus Tan Wei Liang , All Campus Implementation Leads, Mr. Daniel Rodriguez | bar: W1 to W3
| 1.2 | Project Specification Drafting & Approval | Mr. Marcus Tan Wei Liang , Ms. Emily Wong, Steering Committee | bar: W2 to W4
2.0 Tender Process | 2.1 | Prepare RFP & Tender Documentation | Mr. Marcus Tan Wei Liang , Mr. Ahmad Hassan, Mr. Robert Tan | bar: W5
| 2.2 | Vendor Clarification Meetings | Mr. Marcus Tan Wei Liang , Ms. Jennifer Lee | bar: W6
| 2.3 | Vendor Evaluation & Scoring | Steering Committee, Mr. Marcus Tan Wei Liang , Ms. Jennifer Lee, Mr. Robert Tan | bar: W7
| 2.4 | Contract Award & Kick-off | Dr. Michael Chen, Ms. Sarah Thompson, Steering Committee | bar: W8
3.0 Project Governance | 3.1 | Milestone Monitoring Meetings | Mr. Marcus Tan Wei Liang , Steering Committee, Ms. Rachel Tan | bar: W9 to W12
| 3.2 | Risk & Scope Review | Mr. Marcus Tan Wei Liang , Ms. Jennifer Lee, Mr. Robert Tan | bar: W9 to W12
4.0 UAT & Acceptance | 4.1 | UAT Planning & Script Validation | Mr. Marcus Tan Wei Liang , All Campus Implementation Leads, Ms Priya | bar: W11
| 4.2 | UAT Coordination (Multi-Campus) | Mr. Marcus Tan Wei Liang , Ms. Rachel Tan, All Campus Implementation Leads | bar: W12
| 4.3 | Final Acceptance Review | Steering Committee, Mr. Marcus Tan Wei Liang , Ms. Priya Sharma | bar: W13
KEY PERSONNEL
Senior Management | Dr. Michael Chen (Chief Operating Officer), Ms. Sarah Thompson (Project Sponser)
Steering Committee | Mr. David Kumar (Director of Business Development), Dr. Lisa Martinez (Head of Research & Development)
Project Lead | Mr. Marcus Tan Wei Liang
Documentation | Ms. Emily Wong (Product Documentation Specialist)
Finance & Procurement | Mr. Robert Tan (Finance Manager), Mr. Ahmad Hassan (Procurement Manager)
IT & Quality | Ms. Jennifer Lee (Chief Technology Officer), Ms. Priya (Quality Assurance Officer)
Campus Implementation Leads | Dr. Patricia O'Brien (Main), Mr. William Ng (North), Ms. Michelle Lim (East)
Dr. Rajesh Patel (West), Ms. Catherine Smith (South)
Operations & Admin | Mr. Daniel Rodriguez (Operations Manager), Ms. Rachel Tan (Client Relationship Manager)
PROJECT SUMMARY
Total Duration: | 13 weeks
Customer Activities: | 11 tasks
Key Stakeholders: | Steering Committee, Project Lead, Campus Representatives
Project Office: | Staffing, Communications, Infrastructure, Testing Harnesses
PHASE LEGEND:
1.0 Requirements Engineering
2.0 Tender Process
3.0 Project Governance
4.0 UAT & Acceptance